ECDAT — 36-Hour SIH Demo Execution Plan

SIH26164 · NTRO · Corrected demo cut · 2026-09-30

# 1. What this plan is

This is the minimum honest SIH demonstrator. It is not the boundary of the full ECDAT research/product project. The demo should prove the core loop while keeping deeper modules behind clean interfaces.

# 2. The 36-hour schedule

| Time | Phase | What to build |
| --- | --- | --- |
| 0–3 h | Foundation | Repo skeleton, Docker Compose, PostgreSQL, FastAPI, UI shell, replay schema. |
| 3–7 h | Ground truth | Enterprise Lab, planted findings, negative/control cases, expected outputs. |
| 7–12 h | Discovery | Python + Java detection, dependency/lockfile scan, X.509 parsing. |
| 12–15 h | Bounded artifact scan | Static binary imports/symbols/linked libraries; container filesystem/package inspection. No execution. |
| 15–18 h | Evidence fusion | Normalize findings, five evidence roles, confidence, provenance, contradiction display. |
| 18–21 h | Graph | Persist nodes/edges, topology, dependency traversal, blast radius. |
| 21–24 h | Quantum risk | Mosca baseline X+Y>Z, seeded Monte Carlo P(X+Y>Z), visible assumptions. |
| 24–27 h | Migration | Versioned PQC/hybrid registry, role-aware candidates, predicted impact, migration waves. |
| 27–31 h | UI | Overview, scan, inventory, evidence, graph, risk, simulator, reports, replay banner. |
| 31–33 h | CBOM | CycloneDX 1.7 export and validation. |
| 33–34 h | Reliability | Load verified replay snapshot, confirm same API/UI path, freeze API shapes. |
| 34–36 h | Final checks | Benchmark snapshot, security smoke tests, live dry-run, replay dry-run, final pitch run. |

# 3. What the judge should see

Upload a prepared repository or use the staged Enterprise Lab.

Show a finding with source location, evidence role and confidence.

Show a capability-only dependency and a proven usage case as different claims.

Open one asset and traverse its graph dependents.

Open quantum risk and show X, Y, Z, assumptions and probability.

Choose a PQC/hybrid migration candidate and show explicit trade-offs.

Run the simulator and label affected components as predicted impact.

Export a validated CycloneDX 1.7 CBOM.

Switch to replay mode and continue the same UI journey without changing screens.

# 4. What must not be claimed

Complete enterprise coverage of every runtime, cloud KMS/HSM or network protocol.

Deep reverse engineering of arbitrary stripped binaries.

Runtime proof from dependency presence alone.

A fixed year in which a cryptographically relevant quantum computer will arrive.

Guaranteed migration impact; impact is a graph-based prediction until validated.

Benchmark scores that were not actually measured on the saved benchmark artifact.

# 5. Emergency cut order

1. Drop advanced migration-wave optimization first.

2. Keep a simple BFS blast-radius calculation.

3. Keep binary/container support bounded and static.

4. Keep evidence/provenance and capability-vs-usage distinction.

5. Keep replay mode; it is the primary operational fallback.

6. Never replace the live product path with only a screen recording unless every live option has failed.

# 6. Final 30-minute checklist

Run the live demo from a clean reset.

Run the same demo from replay mode.

Open the evidence for the headline finding.

Open graph and blast radius.

Open risk assumptions and probability.

Export and validate CBOM.

Confirm the API contract has not changed.

Save the exact benchmark output and input hashes.

Save the final demo dataset snapshot and its hash.